## Timeline_OMS
Module /Task | IT_Lead | Sub_Module | Command / Details | Dev_Status | Dev_StartDate | Dev_EndDate | Dev_Progress (%) | UAT_TargetDate | UAT_Progress(%) | Remark
ETL | ก้อย | Integration (External System) | 1. Integration to Oracle BI | Pending | 2019-10-06 | 24/06/2019
|  |  | 2. Integration to Seibel | Pending | 24/06/2019 | 2020-03-07
|  |  | 3. Integration to Margento | Pending | 28/06/2019 | 28/06/2019
| หน่อย | Integration (internal System) | 1. DTS013_Officemate_Update CMInvoice | Pending | 2019-01-07 | 26/7/2019
|  |  | 2. DTS027_ERP_Purge_Data Bill Job | Pending | 2019-01-07 | 26/07/2019
|  |  | 3. DTS019_ERP_Update Data DBMaster On CS | Pending | 2019-01-07 | 26/07/2019
|  |  | 4. DTS022_IntranetI_01 Transfer To TBSumCustSale | Pending | 2019-01-07 | 26/07/2019
|  |  | 5. DTS017_Web_Update Status and Tracking (Order)_OFM_Eprocument_CRC | Pending | 2019-01-07 | 26/07/2019
|  |  | 6. DTS025_Web 25 Update CompID Eprocument and T1CardNo On DBMaster | Pending | 2019-01-07 | 26/7/2020
|  |  | 7. DTS026_Web Transfer Invoice AsiaBook | Pending | 2019-01-07 | 26/07/2019
|  |  | 8. DTS021_ERP_Transfer Data To Genesys(DBOutbound) | Pending | 2019-01-07 | 26/07/2019
|  |  | 9. DTS202_Transfer_InvoiceOCI_EproV5_DBMS | Pending | 2019-01-07 | 26/07/2019
|  |  | 10. DTS015_Web_04 Upload Member Rewards | Pending | 2019-01-07 | 26/07/2019
Database | ทราย | SQL Agent job & SP | 1. Insert Data TBARProvision | Pending | 15-05-2019 | 15-06-2019
2. Update IsCutOffOrder
3. JOB_Query MRPoint Daily (มี 3 SP) 3.1 SPC_MRPoint_SI 3.2 SPC_MRPoint_CNFromSRAndCJ 3.3 SPC_MRPoint_CNWrongPriceAndDiscount
4. Update Status SO=Deleted
5. Delete SO Daily
6. Update Reserve ทุกตัว
7. Store procedure ตอนปิดระบบสิ้นเดือน
8. Store procedure ที่ตั้ง job รันทุกวัน ตอนตี 5
9. Update Reserve From TBOnlineDocHead
10. Update Stock ERPProductStatic
| หน่อย + น้องนา | View Table | 1. Vi_CustomerOD | Pending | 15-05-2019 | 15-06-2019
2. Vi_CustomerAR
3. Vi_customerOD1
4. Vi_customerOD2
5. Vi_CustomerOD4
6. Vi_TBCustomerTo_SPOS
7. VI_Customer
8. VI_Contactor
9. VI_Locktelesale
10. Vi_CustomerOD3
11. cmccust
12. cmccustContact
13. cmcshipping
14. cmcbill
15. cmcCheque
16. cmcpayment
17. VI_PriorityOrder
18. vi_agingbycust
19. VISearchCustDateOn
20. Vi_TBcustomerOS
| ทราย + ปุ้ย | Store procedure | spc_OFIN_CostOfGoodsSold_2
SPC_MRPoint_SI
SPC_MRPoint_CNFromSRAndCJ
SPC_MRPoint_CNWrongPriceAndDiscount
sp_DlisingleByDevice
sp_DliAuto
spc_TXTSaleByviewInvoice
spc_ArDetorStat
spc_comsale_up
SPC_MRPoint_SI_RecalB2B
SPC_MRPoint_SI_RecalB2c
spc_OFIN_ReceiptAndAdjust_getLastTrandate
spc_OFIN_ReceiptAndAdjust
spc_TXTSaleByInvNo
spc_OFIN_ReceiptAndAdjust_Reconcile
spc_OFIN_CostOfGoodsSold
SPC_MRPoint_SHOP
SPC_MRPoint_CNFromSRAndCJ_B2B
SPC_MRPoint_CNFromSRAndCJ_B2C
SPC_MRPoint_CNWrongPriceAndDiscount_B2C
SPC_MRPoint_CNWrongPriceAndDiscount_B2B
sp_DliAutoSO_MoveSystem
spc_LockCustomer
sp_DliAutoSO
sp_DliRouteInvSO
sp_DliRouteSRSO
sp_DliRouteOtherSO
spc_DliRouteDLDRSO
spc_InterfaceAutoJV_InputSS
spc_OFIN_SaleAndSaleReturnForReport
spc_InterfaceAutoJV
spc_TXTSaleByInvNo_date
sp_DliRouteCNSO
spc_OFIN_ReceiptAndAdjust_resent
spc_OFIN_SaleAndSaleReturn_delivery
spc_TransferOrderToERP
spc_OFIN_CostOfGoodSoldForReport
spc_OFIN_SaleAndSaleReturn_intoaccountdiscount
spc_OFIN_SaleAndSaleReturn_Special
spc_InterfaceAutoJV_newcost
spc_OFIN_SaleAndSaleReturn_forRecheck
spc_OFIN_ReceiptAndAdjust_forManual
spc_newsalerapt_comup
spc_OFIN_ReceiptAndAdjust_getLastTrandate_forcheck
spc_OFIN_SaleAndSaleReturn
spc_OFIN_ReceiptAndAdjust_getLastTrandate_byReferenceNo
spc_TXTSaleByInvNo_Printing
spc_OFIN_SaleAndSaleReturn_Printting
spc_OFIN_SaleAndSaleReturn_deposittypeC
spc_ArDetorStat
spc_OFIN_CostOfGoodsSold_1
spc_OFIN_ReceiptAndAdjust_3
spc_OFIN_ReceiptAndAdjust_2
spc_OFIN_ReceiptAndAdjust_1
Data | ปุ้ย | Migrate data to New Stucture | 1. tbaccount_master | Pending | 15-05-2019 | 15-06-2019
2. tbcontact_master
3. tbcontact_mapping
4. tbshipping_master
5. tbinvoice_address
6. tbcontact_information
7. tbaccount_additional
8. tbaccount_credit
9. tbfixprice_account
| ปุ้ย | Create View table from New Structure | 1. TBCustMaster | Pending | 15-05-2019 | 15-06-2019
2. TBCustShipping
3. TBCustContact
4. TBCustAdditionContact
5. TBCustContactEmail
6. TBCustomerPhone
7. TBCustInformation
| ปุ้ย | Order | 1. TBSOQUHead | Pending | 15-05-2019 | 15-06-2019
2. TBSOQUDetail
3. SOHead
4. SODetail
5. EOHead
6. EODetail
7. TBBackOrder
| ปุ้ย | Other | 1. TBProductPrintingMaster | Pending | 15-05-2019 | 15-06-2019
2. TBStoreMaster
3. CMTitle
4. TBPOIMaster
5. TBBuildingMaster
6. TbAbbreviationGLAccount
7. TBDVMapZone
8. TBLockTeleSale
9. TBPaidBeforeDelivery
10. TBQCStatusMaster
11. TBQCStatic